## Sheet1
Tiny Totts - Issue List
Sr. No. | Issue | Date | Responsibility | Priority | Status
1 | Home page contents | 2015-05-12 | TinyTotts | Critical | Open
2 | Request for Registration should generate an email | 2015-05-12 | AITSPL | High | Open
3 | Login Page Beautification | 2015-05-12 | AITSPL | Medium | Open
4 | Enable Photographs | 2015-05-12 | AITSPL | Low | Open
5 | Redesign of profile page for user | 2015-05-12 | AITSPL | Medium | Open
6 | Show date validity with name on profile page | 2015-05-12 | AITSPL | Medium | Open
7 | Beautification of Test Start Page | 2015-05-12 | AITSPL | Medium | Open
8 | Do the same changes to single answer test like other | 2015-05-12 | AITSPL | High | Open
9 | Submit Functionality | 2015-05-12 | AITSPL | Critical | Open
10 | Do not show submitted tests on Profile page | 2015-05-12 | AITSPL | Medium | Open
11 | Images for each question | 2015-05-12 | TinyTotts | Critical | Open
12 | Make Bigger Circle for Circle the proper Word test | 2015-05-12 | AITSPL | Medium | Open
13 | words are going out of box | 2015-05-12 | AITSPL | Low | Open
14 | Position review after images are placed | 2015-05-12 | AITSPL | Low | Open
15 | Font size review after images are placed | 2015-05-12 | AITSPL | Low | Open
16 | Answer position review | 2015-05-12 | AITSPL | Low | Open
17 | Code mod if answer is possible to place in two different positions | 2015-05-12 | AITSPL | High | Open
18 | Review padding in all boxes in all questions | 2015-05-12 | AITSPL | Low | Open
19 | Review Answer is Complete logic for all | 2015-05-12 | AITSPL | Medium | Open
20 | Reduce Header space for Admin Profile page | 2015-05-12 | AITSPL | Medium | Open
21 | Admin Menu | 2015-05-12 | AITSPL | Medium | Open
22 | Remove Toolbar from Admin Profile | 2015-05-12 | AITSPL | Medium | Open
23 | User --> Move Add User to top, make it button | 2015-05-12 | AITSPL | Medium | Open
24 | User --> Edit not working | 2015-05-12 | AITSPL | High | Open
25 | Make Edit and Delete same as User for all | 2015-05-12 | AITSPL | Medium | Open
26 | Group --> Edit not working | 2015-05-12 | AITSPL | High | Open
27 | Group should not be deleted where it is assigned to user | 2015-05-12 | AITSPL | High | Open
28 | Make selection based view for content and TestLines, reports | 2015-05-12 | AITSPL | Medium | Open
29 | Change interface for adding new testset line | 2015-05-12 | AITSPL | High | Open
30 | Add paging for testsetline | 2015-05-12 | AITSPL | Low | Open
31 | Make auto logout | 2015-04-30 | AITSPL | Medium | Open
32 | Check login compulsion on all pages | 2015-04-30 | AITSPL | Medium | Open
33 | Make test appear only on valid dates | 2015-04-30 | AITSPL | Medium | Open
34 | Home button for logged in user | 2015-04-30 | AITSPL | Medium | Open